Closeout Procedures

| Project Name | Project Reference Number | Prepared By (print) | Preparer’s Initials |
| --- | --- | --- | --- |
| Customer | Contact | Contact’s Phone # | Date Prepared |

Review Deliverable Requirements and Procedures

| description | Goal | participants | timing | tools and documentation |
| --- | --- | --- | --- | --- |
| Review— Contract deliverable requirements Deliverable acceptance requirements Process for gaining customer acceptance Customer’s direct level of involvement in acceptance process Sign-off procedure | Customer understanding of procedures and acceptance | Project manager Customer project manager | All customer meetings | Contract Customer sign-off procedures Acceptance plan Sign-off checklist |
| Incorporate additional customer provisions as appropriate. |  |  |  |  |

Organize Delivery, Installation, and Testing Requirements

| Description | Goal | Participants | Timing | Tools and Documentation |
| --- | --- | --- | --- | --- |
| Verify that the acceptance plan addresses contract requirements for— Delivery Installation Testing Determine the order in which deliverables will be provided. | Matrix of deliverables | Project manager | Must be completed before customer implementa-tion | Contract Acceptance plan |

Test (As Appropriate)

| Description | Goal | Participants | Timing | Tools and Documentation |
| --- | --- | --- | --- | --- |
| Conduct test Ensure that test evaluates deliverable according to contract criteria Review results Correct deficiencies | Customer signature accepting each deliverable | Project manager Customer project manager | As deliver-ables are completed | Acceptance plan Contract |
| Retest if necessary and document results Describe tests performed Present results Explain unusual results or occurrences |  | Project manager Project team |  | Test report |
| Obtain sign-off if applicable |  | Project manager Customer project manager |  | Customer sign-off procedures |

Post-Test

| Description | Goal | Participants | Timing | Tools and Documentation |
| --- | --- | --- | --- | --- |
| Provide test results Forward acceptance plan review to customer; include test results, request for review and approval, and copy of customer acceptance checklist Specify date by which customer must act to keep project on schedule Ship or install deliverables; customer must sign customer acceptance checklist to verify satisfactory receipt | Invoice to customer | Project manager | Upon completion of each test | Acceptance plan Customer acceptance checklist |
| Forward invoice request and customer acceptance checklist to customer |  | Project manager |  | Invoice initiation request Customer sign-off procedures |